# KST v2 Master Project Checklist

## Project Planning Model

KST v2 will use rolling-wave planning organized by UI section.

Each implementation phase will contain its own:

- UI review

- Field inventory

- Source-data mapping

- Business-rule definition

- Backend design

- Cache design

- API contract

- Frontend implementation

- Export implementation where applicable

- Automated tests

- Legacy comparison

- User acceptance

Later phases may extend or refactor models and services created during earlier phases.

The complete application does not need to be specified field by field before implementation begins.

# Stage 1 — Project Charter

## 1.1 Current-state definition

- Describe KST v1

- Identify the existing Python and PySide6 implementation

- Identify existing report-oriented workflows

- Identify QAD and shortage-database dependencies

- Identify Excel and CSV as current operational outputs

- Identify maintainability and usability limitations

## 1.2 Product vision

- Define KST v2 as a scheduling command console

- Establish the MPS as the primary dashboard

- Establish customer-and-site workspaces

- Establish interactive investigation and drill-down

- Establish controlled planning adjustments

- Preserve required Excel and CSV outputs

- Establish Windows 11 as the primary platform

- Select TypeScript frontend

- Select Tauri and a thin Rust shell

- Select C# and .NET 10 LTS for the backend

- Select ASP.NET Core for the local application API

- Assign business logic, data access, caching, validation, and exports to C#

- Publish the backend as a self-contained win-x64 sidecar

- Use OpenAPI-generated TypeScript API contracts

- Keep Rust limited to Tauri lifecycle, process management, permissions, data directories, and IPC

- Assign business logic and data access to Python

- Assign presentation and interaction state to TypeScript

- Limit Rust to lifecycle, permissions, data directories, and IPC

## 1.3 Users and ownership

- Identify Master Schedulers as primary users

- Identify Planners as primary users

- Identify multiple Keytronic sites

- Define site-specific customer responsibility

- Identify David as project owner and final product decision maker

- Define consultation with other schedulers

- Preserve owner authority over final design decisions

## 1.4 Scope

- Interactive MPS dashboard

- Part and work-order investigation

- Component and shortage investigation

- Purchase-order and buyer information

- Open-order investigation

- Planning and staged changes

- Finished-goods visibility

- Configurable reports and exports

- Customer-and-site configuration

- Historical shipment capability

- Legacy Simulation compatibility

- Windows desktop deployment

- Testing and maintainability documentation

## 1.5 Out of scope

- Direct QAD database writes

- Direct writes to other company databases

- User accounts and login

- Authorization and permission systems

- Approval workflows

- Centralized user profiles

- Replacing QAD

- Replacing other departments’ systems

- Universal business-intelligence platform

- Advanced Simulation redesign in Release 1

- Cloud service dependency

## 1.6 Safety and integration boundaries

- Use database-level read-only credentials

- Use Windows credentials for QAD access

- Use application-specific read-only shortage-database credentials

- Produce human-reviewable update files

- Never claim that exported updates were applied

- Keep QAD-specific schemas behind adapters

- Preserve stable domain and API contracts

- Identify the expected 2027 QAD upgrade as a major risk

## 1.7 Release and rollout

- Define Release 1 as a complete operational replacement

- Avoid reducing Release 1 to a thin demonstration MVP

- Deploy first at the primary site

- Keep KST v1 available during pilot

- Define a three-to-six-month pilot period

- Validate with active schedulers

- Deploy to other sites incrementally

- Define pilot-exit criteria

- Approve the Project Charter

Stage 1 status: Complete

# Stage 2 — Legacy System and Product Inventory

## 2.1 Legacy capability census

- Component MRP

- WO Variance

- Master Plan

- MPS

- Shipments-To-Go

- Open Orders

- Shortage Report

- S&OP

- Simulation

- Settings and shared behavior

## 2.2 Migration disposition

- Reject one-to-one report migration

- Establish the dashboard as the product’s central experience

- Absorb Component MRP into dashboard drill-down and export

- Absorb WO Variance into work-order detail

- Absorb Shortage Report into dashboard investigation and export

- Integrate Open Orders into customer and planning workflows

- Redesign Master Plan as the Planning Workbook

- Retain Shipments-To-Go as an Excel-only report

- Retain S&OP as an Excel-only report

- Retain Simulation substantially as-is for Release 1

- Add Historical Shipments as a new capability

## 2.3 Prototype inventory

- Treat the HTML prototype as the working product specification

- Inventory the application shell

- Inventory customer tabs and workspaces

- Inventory the MPS grid

- Inventory part information

- Inventory work-order detail

- Inventory kitting and variance

- Inventory immediate shortages

- Inventory future shortages

- Inventory components

- Inventory PO drill-down

- Inventory multi-part shortages

- Inventory Planning Workbook

- Inventory customer Open Orders

- Inventory Finished Goods

- Inventory general Open Orders

- Inventory general WO Variance

- Inventory report-generation screens

- Create the prototype field-inventory workbook

## 2.4 Dataset inventory

- Inventory QADPRO2 tables

- Inventory Analysis database tables

- Inventory keytronicshortage tables

- Inventory stored procedures

- Inventory important CTEs

- Identify the planning dataset group

- Identify the sales-order dataset group

- Identify the shortage and BOM dataset group

- Identify the pricing dataset group

- Identify the WO Variance dataset group

- Identify the inspection and qualification dataset group

- Identify high-use datasets

- Identify candidate cache datasets

- Create the initial UI-to-source mapping

## 2.5 MPS source decision

- Review sp_QAD_ktmpswkm

- Identify its parameters

- Identify its source tables

- Identify its part filters

- Identify its planner and product-line filters

- Identify supply classifications

- Identify falldown behavior

- Identify weekly pivot behavior

- Decide not to obtain the original Progress source

- Retain the working SQL procedure initially

- Keep the stored procedure behind a QAD adapter

- Normalize pivoted results into application records

- Cache normalized results in the backend snapshot

- Do not expose the procedure result directly to TypeScript

- Make future replacement possible without changing the frontend contract

## 2.6 Planning-method revision

- Identify repeated fields and shared concepts

- Recognize that deep drill-down requirements will emerge during implementation

- Replace full up-front field planning with rolling-wave planning

- Organize implementation by UI section

- Define each UI section as a vertical slice

- Retain the field inventory as a living traceability tool

- Define shared abstractions only after real repeated use

- Establish a consistent checklist for every UI phase

Stage 2 status: Broad inventory complete; detailed lineage now occurs inside each UI phase

# Stage 3 — Technical Foundation

This stage establishes the minimum architecture required before feature slices begin.

## 3.1 Repository structure

- Create the final repository layout

- Create frontend workspace

- Create Tauri shell

- Create Python backend package

- Create shared documentation structure

- Create test directories

- Create sample-data and fixture directories

- Create migration and architecture decision directories

- Add formatting and linting configuration

- Add type-checking configuration

## 3.2 Development environment

- Select and document the supported .NET 10 SDK patch

- Target net10.0

- Create solution and project files

- Configure nullable reference types

- Configure analyzers and formatting

- Configure NuGet package policy

- Add Microsoft.Data.SqlClient

- Add Dapper

- Select Excel workbook library

- Configure ASP.NET Core local API

- Configure OpenAPI generation

- Configure TypeScript client generation

- Configure self-contained win-x64 publishing

- Configure single-file publication where compatible

- Keep trimming disabled initially

- Keep Native AOT disabled initially

## 3.3 Backend process lifecycle

- Define how Tauri starts the .NET sidecar

- Define backend health check

- Define backend shutdown behavior

- Define abnormal-exit recovery

- Define logging paths

- Define temporary-file paths

- Define local configuration paths

- Define export paths

- Define port or IPC allocation

- Prevent duplicate backend processes

- Define how Tauri locates and starts the packaged .NET executable

- Define loopback port selection

- Define health and readiness checks

- Define graceful shutdown

- Define forced termination after timeout

- Prevent duplicate backend instances

- Capture backend stdout/stderr safely

- Package the backend as a Tauri external binary

- Test lifecycle using a published self-contained executable, not only dotnet

## 3.4 API foundation

- Create Kst.Api ASP.NET Core project

- Bind only to loopback

- Define /health

- Define /ready

- Define API versioning conventions

- Define Problem Details error responses

- Define JSON naming and serialization rules

- Define date, time, decimal, and enum serialization

- Generate OpenAPI

- Generate TypeScript DTOs or client

- Add API contract tests

- Ensure substantive business rules remain outside controllers/endpoints

## 3.5 Database foundation

- Microsoft.Data.SqlClient

- Dapper

- Explicit parameterized SQL

- Explicit stored-procedure adapters

- Windows-integrated QAD authentication

- Read-only shortage-database credential

- Async query execution

- Connection pooling

- Cancellation tokens

- Command timeouts

- Strongly typed integration result records

- No Entity Framework model of QAD

- No application migrations against QAD-owned schemas

## 3.6 Snapshot and cache foundation

- Define immutable or controlled snapshot records

- Define thread-safe snapshot replacement

- Define per-customer/site cache keys

- Define concurrent refresh behavior

- Define cancellation during application shutdown

- Define DateTimeOffset timestamps

- Define source-status records

- Define stale and partial-result states

- Preserve the last successful snapshot after failure

- Measure memory use under realistic customer loads

## 3.7 Testing foundation

- Select .NET test framework

- Create unit-test projects

- Create integration-test projects

- Create architecture tests for project dependencies

- Create adapter fixtures

- Create SQL result fixtures

- Create stored-procedure parser fixtures

- Create golden-master workbook tests

- Create ASP.NET Core API integration tests

- Create OpenAPI contract tests

- Retain TypeScript unit and component tests

- Test the packaged Tauri + .NET walking skeleton early

## 3.8 Observability

- Define structured backend logging

- Define frontend logging

- Add correlation or request IDs

- Log query duration without exposing sensitive data

- Log snapshot refresh duration

- Log export generation

- Add user-readable error summaries

- Add detailed diagnostic logs

- Define log retention and cleanup

Stage 3 completion gate: The desktop shell can start and stop the Python backend, connect safely to configured data sources, serve a typed health response, and manage an empty customer/site snapshot.

# Stage 4 — Phase 1: Application Shell and Workspace Configuration

## 4.1 UI behavior review

- Review the shell prototype

- Confirm top application bar behavior

- Confirm customer-tab behavior

- Confirm General-tab behavior

- Confirm theme behavior

- Confirm accent-color behavior

- Confirm row-density behavior

- Confirm bottom action-bar behavior

- Confirm refresh and status presentation

- Confirm local persistence expectations

## 4.2 Field inventory

- Filter workbook to Global Shell and Customer Workspace fields

- Map application-owned fields

- Map customer identifiers

- Map site identifiers

- Map planner display data

- Map lead-time display data

- Map active-part counts

- Map shortage counts

- Identify fields that remain local-only

- Add any missing prototype fields

## 4.3 Customer-and-site configuration

- Define CustomerSiteAssignment

- Define site

- Define customer code and display name

- Define product-line filters

- Define planner filters

- Define active-part filters if needed

- Support one customer at multiple sites

- Support temporary customer coverage

- Define add, edit, reorder, enable, and remove behavior

- Define validation

- Persist locally

## 4.4 Snapshot status

- Define not-loaded state

- Define loading state

- Define current state

- Define stale state

- Define partially refreshed state

- Define failed state

- Display last successful refresh

- Display source-level warnings

- Preserve cached data after failed refresh

## 4.5 Backend and API

- Create workspace configuration service

- Create local settings service

- Create application status service

- Create source-status model

- Create workspace-list endpoint

- Create workspace-update endpoint

- Create preferences endpoints

- Create health and status endpoints

## 4.6 Frontend

- Build top application bar

- Build customer tabs

- Build General tab

- Build customer header

- Build theme control

- Build accent control

- Build density control

- Build source-status indicator

- Build refresh action shell

- Build confirmation dialog

- Build toast notifications

## 4.7 Validation

- Test local settings persistence

- Test customer/site distinction

- Test temporary coverage

- Test corrupted local configuration

- Test empty workspace

- Test backend unavailable state

- Test failed refresh state

- Owner acceptance

Phase 1 completion gate: The user can configure and switch among site-specific customer workspaces, and the shell correctly displays backend and snapshot status.

# Stage 5 — Phase 2: MPS Dashboard Grid

## 5.1 UI behavior review

- Confirm the MPS grid layout

- Confirm sticky part columns

- Confirm horizontal scrolling

- Confirm weekly horizon options

- Confirm fiscal period and quarter bands

- Confirm release-date and due-date modes

- Confirm status colors and symbols

- Confirm empty bucket behavior

- Confirm row selection

- Confirm week-cell selection

- Confirm full-grid and collapsed-grid transitions

- Confirm refresh behavior

## 5.2 Field inventory and lineage

- Complete all MPS grid field mappings

- Map part number

- Map description

- Map customer and site

- Map planner

- Map product line

- Map part status

- Map runtime standard

- Map planned supply

- Map firm or regular supply

- Map falldown

- Map week start

- Map fiscal period

- Map fiscal quarter

- Map fiscal year

- Map status summary inputs

- Add fields discovered during real-data inspection

## 5.3 Stored-procedure adapter

- Implement sp_QAD_ktmpswkm execution

- Map customer/site assignment to procedure parameters

- Support multiple calls for non-contiguous filters

- Validate fixed columns

- Detect dynamic week columns

- Parse week-column dates

- Parse falldown

- Preserve SUPPLY and PLANNED

- Preserve site context

- Normalize numeric values

- Deduplicate merged calls

- Record procedure execution metadata

- Handle malformed results

## 5.4 Calendar service

- Define week-start convention

- Define fiscal calendar source

- Define fiscal period boundaries

- Define fiscal quarter boundaries

- Define fiscal year boundaries

- Support up to 72 weeks

- Test year transitions

- Test fiscal-period transitions

- Test leap years

- Test falldown boundary

## 5.5 Schedule models and rules

- Define PartSchedule

- Define ScheduleBucket

- Define supply classifications

- Preserve procedure source type

- Define scheduled-quantity display

- Define work-order summary placeholders

- Define shortage summary placeholders

- Define Released status

- Define Frozen status

- Define Allocating status

- Define Shortage status

- Define Empty status

- Separate prototype styling rules from confirmed business rules

## 5.6 Cache and API

- Add MPS data to customer/site snapshot

- Define initial dashboard endpoint

- Define horizon parameter

- Define release/due basis parameter

- Return normalized week records

- Return snapshot metadata

- Return source warnings

- Avoid 72 dynamic API properties

- Test snapshot reuse across tab switching

## 5.7 Frontend

- Implement fiscal bands

- Implement week headers

- Implement part rows

- Implement quantity cells

- Implement status styling

- Implement horizon selector

- Implement release/due selector

- Implement row selection

- Implement week selection

- Implement loading skeleton

- Implement empty customer state

- Implement stale-data warning

- Implement refresh feedback

## 5.8 Validation

- Compare normalized data with procedure output

- Compare totals by part

- Compare planned totals

- Compare supply totals

- Compare falldown totals

- Verify product-line filtering

- Verify planner filtering

- Verify site filtering

- Verify multiple procedure-call merge

- Validate representative customers

- Validate 12-week view

- Validate 72-week view

- Owner acceptance

Phase 2 completion gate: A scheduler can open a customer/site workspace and use a validated, cached MPS grid for schedule review.

# Stage 6 — Phase 3: Part Information Drill-Down

## 6.1 UI and fields

- Confirm the Part Info tab

- Map revision

- Map planner

- Map lead time

- Map UOM

- Map item class

- Map description

- Map component count

- Map on-hand finished goods

- Map WIP

- Map safety stock

- Map part-level schedule status

## 6.2 Backend

- Create part-master adapter

- Create site-planning-parameter adapter

- Define effective planner fallback

- Define effective lead-time fallback

- Define inventory summary

- Define WIP calculation

- Define component count

- Create PartDetail

- Create part-detail endpoint

- Cache stable part information where appropriate

## 6.3 Frontend and validation

- Build Part Info panel

- Build loading state

- Build missing-part state

- Build partial-data warnings

- Validate against QAD

- Validate fallback behavior

- Owner acceptance

Phase 3 completion gate: Selecting an MPS part displays validated part attributes and inventory summaries.

# Stage 7 — Phase 4: Work Orders and Kitting

## 7.1 Field and rule discovery

- Map work-order number

- Map ordered quantity

- Map completed quantity

- Map open quantity

- Map status

- Map start date

- Map due date

- Map production line

- Identify allocation fields

- Define kitting percentage

- Map component requirements

- Map issued quantities

- Define variance quantity

- Define variance percentage

- Confirm severity thresholds

## 7.2 Backend

- Create work-order adapter

- Create WO-material adapter

- Define WorkOrderSummary

- Define WorkOrderMaterialLine

- Create work-order service

- Create kitting service

- Create variance service

- Join work orders to schedule buckets

- Add work-order summaries to cached MPS data or lazy detail

- Create work-order endpoints

## 7.3 Frontend and validation

- Build work-order cards

- Build selected-week filtering

- Build all-open-WO view

- Build kitting expansion

- Build variance sorting

- Build no-WO state

- Compare against WO Variance report

- Validate partial issue

- Validate over-issue

- Validate completed work orders

- Owner acceptance

Phase 4 completion gate: A scheduler can trace an MPS bucket to its work orders and component issue status.

# Stage 8 — Phase 5: Component and BOM Detail

## 8.1 Field and rule discovery

- Map component part

- Map component description

- Map quantity per

- Define extended requirement

- Map component on hand

- Map incoming supply

- Define coverage percentage

- Define material status

- Confirm BOM revision and effective-date behavior

- Confirm multi-level BOM expectations

- Confirm phantom and substitute behavior

## 8.2 Backend

- Create BOM adapter

- Create BOM-explosion service

- Define ComponentRequirement

- Define required quantity grain

- Add inventory availability service

- Add component supply summary

- Create component endpoint

- Decide when pre-exploded BOM storage is justified

- Add BOM tests

## 8.3 Frontend and validation

- Build Components tab

- Build component selection

- Build coverage display

- Build no-components state

- Compare against Component MRP

- Validate multi-level quantities

- Validate duplicate components

- Owner acceptance

Phase 5 completion gate: A scheduler can inspect the material structure and coverage behind a scheduled parent part.

# Stage 9 — Phase 6: Immediate Shortages

## 9.1 Rule definition

- Confirm immediate window length

- Define required quantity

- Define available quantity

- Define nettable inventory statuses

- Define shortage quantity

- Define On Hand status

- Define Due This Week status

- Define Short status

- Define work-order association

- Define receipt timing assumptions

- Define inventory allocation assumptions

- Define treatment of shared inventory

## 9.2 Backend

- Define ImmediateShortage

- Create immediate-requirement service

- Create inventory-netting service

- Create immediate-PO-coverage service

- Create shortage-classification service

- Add shortage counts to MPS buckets

- Create immediate-shortage endpoint

- Add stale-source warnings

## 9.3 Frontend and validation

- Build Shortages tab

- Sort components by severity

- Build status indicators

- Build component selection

- Build no-immediate-WO state

- Compare with existing Shortage Report

- Validate receipt boundary

- Validate insufficient incoming supply

- Validate fully covered requirements

- Owner acceptance

Phase 6 completion gate: A scheduler can identify immediate component shortages affecting near-term work orders.

# Stage 10 — Phase 7: Purchase-Order Drill-Down

## 10.1 Field discovery

- Map PO number

- Map vendor

- Map ordered quantity

- Map open quantity

- Map due date

- Map confirmed or scheduled status

- Map buyer

- Define PO coverage

- Map shortage comment

- Map supplier credit-hold flag

- Map CIA flag

- Confirm multiple-PO ordering

## 10.2 Buyer-note decision

- Confirm authoritative note source

- Determine whether KST may update ShortageMaster

- If writes are prohibited, define read-only behavior

- Evaluate local-only note storage

- Evaluate export-based note updates

- Define conflict and refresh behavior

- Document final persistence decision

## 10.3 Backend and frontend

- Create PO adapter

- Create vendor adapter

- Create supplier-risk adapter

- Create note adapter

- Define ComponentPurchaseOrder

- Create PO-coverage service

- Create PO-detail endpoint

- Build Component PO Drill card

- Build previous/next PO navigation

- Build buyer-note interaction

- Build no-open-PO state

- Validate with current shortage output

- Owner acceptance

Phase 7 completion gate: A scheduler can trace a component shortage to its open purchase orders, vendor, coverage, and current buyer information.

# Stage 11 — Phase 8: Future Shortages and Component MRP

## 11.1 Rule discovery

- Define projection horizon

- Define lead-time horizon

- Define projected balance

- Define planned-order handling

- Define covering PO

- Define projected clear week

- Define coverage gap

- Define future-shortage quantity

- Confirm behavior when no WO exists

- Confirm forecast treatment

## 11.2 Backend

- Define ProjectedShortage

- Create time-phased Component MRP service

- Create projected-balance service

- Create future-shortage service

- Reuse component and PO services

- Create future-shortage endpoint

- Create Component MRP endpoint

- Define Component MRP export dataset

## 11.3 Frontend, export, and validation

- Build Future Shortages tab

- Build projection descriptions

- Build no-future-shortage state

- Build Component MRP export options

- Support selected parent parts

- Support selected components

- Support date horizon

- Support selectable columns

- Compare with existing Component MRP

- Owner acceptance

Phase 8 completion gate: A scheduler can see future material exposure and export a scoped Component MRP report.

# Stage 12 — Phase 9: Multi-Part Shortage Analysis

## 12.1 Selection behavior

- Confirm Multi mode

- Confirm row checkbox behavior

- Confirm one-part WO-centric view

- Confirm multi-part component-centric view

- Confirm affected-parent display

- Confirm selection clearing

- Confirm export scope

## 12.2 Rules and backend

- Define shared-component aggregation

- Define inventory netting across selected parents

- Prevent duplicate inventory multiplication

- Define work-order-specific shortage grain

- Define component-centric shortage grain

- Define affected-parent relationships

- Create selection-analysis endpoint

- Create shortage export request

- Create configurable shortage export dataset

## 12.3 Frontend and validation

- Build Multi selection

- Build WO-centric table

- Build part-centric table

- Build shared-component pills

- Build export dialog

- Support selected columns

- Support selected parts and WOs

- Validate shared inventory

- Compare exported results with current Shortage Report

- Owner acceptance

Phase 9 completion gate: A scheduler can analyze and export shortages for one or several selected MPS parent parts.

# Stage 13 — Phase 10: Planning Workbook

## 13.1 Field and rule discovery

- Map sales-order quantities

- Map forecast quantities

- Map MPS quantities

- Map unit price

- Map unit cost

- Define SO value

- Define MPS value

- Define demand selection

- Define estimated on-hand

- Define adjusted on-hand

- Define adjustment grain

- Define frozen-fence restrictions

- Define validation rules

- Define export mappings

## 13.2 Backend

- Define PlanningBucket

- Define ProposedMpsAdjustment

- Create planning-data service

- Create inventory-projection service

- Create price and cost adapters

- Create adjustment staging service

- Create validation service

- Create planning endpoints

- Create MPS mass-update exporter

## 13.3 Frontend and validation

- Build Planning Workbook grid

- Build grouped part blocks

- Build editable adjustment row

- Highlight staged changes

- Build clear confirmation

- Build export behavior

- Display last export

- Test negative inventory

- Test frozen periods

- Test invalid adjustments

- Validate exported mass update

- Owner acceptance

Phase 10 completion gate: A scheduler can review supply and demand, stage MPS adjustments, validate them, and produce a QAD-compatible update file.

# Stage 14 — Phase 11: Customer Open Orders

## 14.1 Field inventory and rules

- Map sales-order number

- Map customer PO

- Map line

- Map item and revision

- Map ship date

- Map perform date

- Map required date

- Map dock date

- Map on hand

- Map extended price

- Map ship-to

- Map order status

- Confirm editable date fields

- Define date validation

- Define QXtend mapping

## 14.2 Backend

- Create sales-order adapter

- Define OpenOrderLine

- Define ProposedOrderChange

- Create customer Open Orders service

- Create order-change validation

- Create Open Orders endpoints

- Create QXtend-compatible exporter

## 14.3 Frontend and validation

- Build customer order grid

- Build editable date cells

- Highlight staged changes

- Build clear confirmation

- Build export behavior

- Display change count

- Validate representative orders

- Validate output file with QXtend requirements

- Owner acceptance

Phase 11 completion gate: A scheduler can inspect customer orders and generate validated date-change files without direct database writes.

# Stage 15 — Phase 12: Finished Goods

## 15.1 Field and rule discovery

- Define as-of date

- Map due orders

- Map due units

- Map finished-goods on hand

- Map location

- Map lot

- Define shipping locations

- Define hold locations

- Define RMA classification

- Define nettable status

- Define inventory value

- Define demand coverage

## 15.2 Backend and frontend

- Create finished-goods adapter

- Create lot adapter

- Create inventory-status adapter

- Define FinishedGoodsPosition

- Create coverage service

- Create Finished Goods endpoint

- Build summary cards

- Build location and lot grid

- Build date selector

- Build export if retained

- Validate nettable inventory

- Validate RMA exclusion

- Owner acceptance

Phase 12 completion gate: A scheduler can determine whether available finished goods cover immediate customer demand.

# Stage 16 — Phase 13: General Open Orders

## 16.1 Search design

- Confirm all filters

- Confirm required versus optional filters

- Confirm default site behavior

- Confirm result limits

- Confirm sorting behavior

- Confirm selectable columns

- Confirm column order

- Confirm saved layouts

- Confirm export behavior

## 16.2 Backend and frontend

- Define OpenOrderSearchRequest

- Define OpenOrderSearchRow

- Create cross-customer search service

- Add filter validation

- Add pagination or safe result limits

- Create search endpoint

- Create configurable export

- Build filter bar

- Build column builder

- Build sortable grid

- Build saved layouts

- Validate large result sets

- Owner acceptance

Phase 13 completion gate: A scheduler can perform flexible cross-customer Open Orders searches and exports.

# Stage 17 — Phase 14: General WO Variance

## 17.1 Rules and backend

- Confirm IOS-code filter

- Confirm included WO statuses

- Confirm component inclusion

- Confirm variance thresholds

- Confirm negative-variance treatment

- Define WorkOrderVarianceRow

- Create cross-customer variance service

- Create search endpoint

- Decide whether export remains required

## 17.2 Frontend and validation

- Build IOS selector

- Build sortable variance grid

- Build severity highlighting

- Build empty state

- Build export if retained

- Compare with current WO Variance report

- Owner acceptance

Phase 14 completion gate: A scheduler can independently investigate work-order material variance by IOS or equivalent scope.

# Stage 18 — Phase 15: Standalone Excel Reports

## 18.1 Shared report infrastructure

- Define report request pattern

- Define output-directory behavior

- Define filename conventions

- Define overwrite behavior

- Define workbook metadata

- Define progress reporting

- Define cancellation behavior

- Define error cleanup

- Define workbook validation tests

## 18.2 Shipments-To-Go

- Inventory current inputs

- Inventory current output columns

- Map every output field

- Extract business rules

- Reuse shared order and shipment services

- Implement workbook generation

- Compare with legacy workbook

- Validate with stakeholders

- Owner acceptance

## 18.3 S&OP

- Inventory current inputs

- Inventory current output columns

- Determine use of MPS procedure data

- Extract aggregation rules

- Implement workbook generation

- Compare with legacy workbook

- Validate monthly period behavior

- Owner acceptance

Phase 15 completion gate: Required Shipments-To-Go and S&OP workbooks can be generated and validated from KST v2.

# Stage 19 — Phase 16: Historical Shipments

## 19.1 Requirements

- Confirm user questions

- Confirm retention horizon

- Confirm customer and site filters

- Confirm part filters

- Confirm date-range behavior

- Confirm order and PO fields

- Confirm shipment quantity

- Confirm revenue calculation

- Confirm returns and reversals

- Confirm corrections

- Decide export requirements

## 19.2 Backend and frontend

- Investigate tr_hist

- Identify authoritative shipment transactions

- Define ShipmentHistoryRow

- Create transaction normalization

- Create reversal handling

- Create shipment-history endpoint

- Build search and results UI

- Build drill-downs if needed

- Build export if approved

- Validate historic totals

- Owner acceptance

Phase 16 completion gate: A scheduler can review reliable historical shipment activity for a selected site, customer, part, and date range.

# Stage 20 — Phase 17: Legacy Simulation

## 20.1 Compatibility inventory

- Document current input format

- Document current calculation process

- Document current output

- Identify external file dependencies

- Identify PO data requirements

- Identify configuration requirements

- Identify known limitations

## 20.2 Migration

- Move existing logic behind the v2 backend

- Preserve existing inputs

- Preserve existing outputs

- Add regression fixtures

- Build minimal v2 UI integration

- Add errors and progress reporting

- Validate against KST v1

- Owner acceptance

## 20.3 Deferred redesign

- Record advanced simulation as future scope

- Create future-requirements placeholder

- Avoid designing the advanced simulation engine during Release 1

- Avoid allowing legacy architecture to constrain future simulation design

Phase 17 completion gate: Existing Simulation functionality is available without expanding Release 1 scope.

# Stage 21 — Cross-Cutting Export Completion

Some export work occurs inside feature phases, but this stage verifies the export system as a whole.

- MPS configurable Excel export

- Component MRP configurable Excel export

- Shortage configurable Excel export

- Open Orders export

- Finished Goods export if retained

- WO Variance export if retained

- MPS mass-update CSV

- Sales-order mass-update CSV

- Shipments-To-Go workbook

- S&OP workbook

- Historical Shipments export if approved

- Consistent filenames

- Consistent destination handling

- Consistent error handling

- Selected-column support

- Selected-part support

- Selected-date support

- Workbook formatting standards

- Export audit metadata

- Golden-master validation

# Stage 22 — Cross-Cutting Quality and Hardening

## 22.1 Data integrity

- Verify domain filtering

- Verify site filtering

- Verify customer assignments

- Verify product-line filtering

- Verify planner filtering

- Verify date boundaries

- Verify numeric precision

- Verify null handling

- Verify duplicate handling

- Verify stale-data handling

- Verify partial-refresh handling

## 22.2 Performance

- Measure startup time

- Measure initial customer load

- Measure refresh time

- Measure drill-down time

- Measure 72-week MPS rendering

- Measure large Open Orders search

- Measure shortage analysis

- Measure export generation

- Add indexes or query changes where allowed

- Add in-memory caching where measured

- Reconsider persistent cache only if justified

- Reconsider pre-exploded BOM only if justified

## 22.3 Reliability

- Test QAD unavailable

- Test shortage DB unavailable

- Test Analysis DB unavailable

- Test one source failing during refresh

- Test backend crash recovery

- Test corrupted local settings

- Test interrupted export

- Test invalid destination

- Test low disk space

- Test application update compatibility

## 22.4 Security

- Verify read-only QAD access

- Verify read-only shortage access unless an exception is approved

- Prevent credentials in logs

- Protect local configuration

- Bind API only to the local machine

- Validate all file paths

- Sanitize filenames

- Validate all user-entered filters

- Validate staged update values

- Ensure no direct company-database writes exist

## 22.5 Accessibility and usability

- Keyboard navigation

- Visible focus state

- Color-independent status indicators

- Light and dark mode readability

- Compact and comfortable density

- Scaling on common Windows resolutions

- Horizontal-grid usability

- Loading feedback

- Clear empty states

- Clear stale-data warnings

- Clear export confirmation

- User testing with schedulers

## 22.6 Documentation

- Architecture overview

- Repository guide

- Developer setup

- Database-source catalog

- Business-rule catalog

- API documentation

- Cache and refresh documentation

- Export documentation

- Deployment guide

- Troubleshooting guide

- Scheduler user guide

- QAD-upgrade migration guide

- Architecture decision records

# Stage 23 — Release 1 Readiness

## 23.1 Functional readiness

- All required interactive phases complete

- Required exports complete

- Simulation compatibility complete

- Historical Shipments disposition confirmed

- Customer/site configuration complete

- Staged update workflows complete

- No direct database writes

- All critical business rules approved

## 23.2 Validation readiness

- Golden-master comparisons complete

- Representative customer tests complete

- Representative site tests complete

- Scheduler walkthroughs complete

- Known intentional differences documented

- Open critical defects resolved

- Performance targets accepted

- Error behavior accepted

## 23.3 Packaging and deployment

- Build signed or approved Windows installer

- Package .NET sidecar

- Package runtime dependencies

- Configure installation directories

- Configure local settings migration

- Configure logging directories

- Configure update strategy

- Test clean installation

- Test upgrade installation

- Test uninstall

- Create deployment instructions

## 23.4 Operational readiness

- Identify pilot users

- Identify support contacts

- Define defect-reporting process

- Define fallback to KST v1

- Define issue severity

- Define data-validation process

- Define training

- Define feedback collection

- Define release notes

- Approve pilot launch

# Stage 24 — Pilot

## 24.1 Initial-site pilot

- Deploy at primary site

- Keep KST v1 available

- Monitor data discrepancies

- Monitor refresh reliability

- Monitor export compatibility

- Monitor performance

- Capture scheduler feedback

- Capture missed fields and workflows

- Correct critical business rules

- Refine UI

- Refine diagnostics

## 24.2 Pilot exit criteria

- Core workflows used successfully

- Required reports accepted

- Mass-update files accepted

- No unresolved critical data errors

- No unresolved direct-write risk

- Refresh reliability accepted

- Performance accepted

- User acceptance received

- Support process functioning

- Project owner approves broader rollout

# Stage 25 — Incremental Multi-Site Rollout

- Select next site

- Gather site-specific configuration

- Validate customer assignments

- Validate planner mappings

- Validate product-line mappings

- Validate database access

- Validate reports

- Validate local operating practices

- Train users

- Deploy

- Monitor

- Repeat for each site

- Retire KST v1 only after approved transition

# Stage 26 — Post-Release Roadmap

## 26.1 QAD upgrade preparation

- Monitor upgrade timeline

- Obtain test-schema access

- Compare QAD table changes

- Update adapters

- Preserve domain models

- Preserve API contracts

- Run migration fixtures

- Validate exports

- Deploy compatibility update

## 26.2 Advanced Simulation

- Gather scheduler requirements

- Define simulation questions

- Define scenario inputs

- Define authoritative source data

- Define constraints

- Define calculation model

- Define validation model

- Define comparison views

- Define saved scenarios

- Create separate charter and implementation plan

## 26.3 Potential future enhancements

- More historical analytics

- Additional configurable exports

- Additional cross-customer views

- Improved coverage and risk modeling

- Alternate-part analysis

- Expanded supplier-risk integration

- Additional local-first capabilities

- Site-requested enhancements

# Current Project Position

## Completed

- Stage 1 — Project Charter

- Stage 2 — Broad legacy, UI, and dataset inventory

- MPS source strategy

- Rolling-wave phased-planning decision

- Prototype field-inventory workbook

## Current focus

- Finish only the fields needed for Phase 1 and Phase 2

- Establish the technical foundation

- Implement Application Shell and Workspace Configuration

- Implement the MPS Dashboard Grid

## Planning rule going forward

Before beginning each later phase:

- Review that section of the prototype.

- Filter the field inventory to that phase.

- Map the fields currently known.

- Add missing fields discovered during review.

- Confirm business rules.

- Define the smallest sufficient backend contract.

- Implement and validate the complete vertical slice.

- Update the shared models only when the implemented phase proves that an extension is needed.